## Sheet1
Task | # hours (expected) | # hours (Actual) | Contributer(s) | Status
Set up github repo | 1 | 0.25 | Jackson B | Complete
Initialize github pages project website | 1 | 0.25 | Jackson B | Complete
Create personal bio | 2 | 2.5 | All members | Complete
Initial project scoping | 2 | 3 | All members | Complete
Create ER Diagram | 1 | 1 | Cole K | Complete
configure dev env | 1 | 2 | All members | Complete
Initialize backend | 8 | 10 | Jackson B, Cole K, Cole M | Complete
configure docker | 8 | 6 | Jackson B, Cole K, Cole M | Complete
initialize frontend | 5 | 3.5 | Cole M, Cole K | Complete
student model | 1 | 2 | Cole K | Complete
sponsor model | 1 | 0.5 | Jackson B | Complete
assignment model | 1 | 3 | Gates A | Complete
preference model | 1 | 2.5 | Thomas H | Complete
project model | 1 | 1 | Jackson B | Complete
CRUD Models | 5 | 2 | Cole K, Thomas H, Gates A | Nixed (Admin will CRUD most objects from Django admin page)
import student CSV | 2 | 2 | Jackson B | Complete
Clean up repo | 1 | 1 | Jackson B, Cole K, Cole M | Complete
Frontend page structure | 1 | 1 | Cole M | Complete
Project description pages | 2 | 2 | Cole M, Cole K | Complete
Form filling structure | 2 |  | Cole M | In Progress
Attachment model | 1 |  | Jackson B | In Progress
(front end) edit/add-project fuctionality | 1 | NA | Cole K | In Progress
Integrate AI with Project | 0.5 |  | Cole K | In Progress