## Sprint 2 Deliverables
Task | # hours (expected) | # hours (Actual) | Contributer(s) | Status
Form filling structure | 2 | 2 | Cole M, Gates A | Complete
Attachment model | 3 |  | Jackson B | In Progress
(front end) edit/add-project fuctionality | 1 | NA | Cole K | In Progress
Integrate AI with Project | 0.5 | 0.5 | Cole K | Done
Sponsor Workflow | 5 | 3 | Thomas H, Cole M | In Progress
Student Workflow | 6 | 7 | Cole M | Complete
Email Client | 4 | 5 | Gates A | Complete
Oauth | 3 | 2 | Cole K | Complete
Interface Design | 4 | 5 | Cole M, Gates A | In Progress
Cloud Deployment | 2 | 6 | Cole K | Complete
Backend Unit Testing | 3 | 5 | Jackson B | Complete
Model Refactoring | 3 | 5 | Jackson B | Complete
API Refactoring (Bug fixes, endpoint creation) | 3 | 5 | Jackson B | Complete
Student Oauth Through My Bama | 5 | 2 | Cole K | Reassigned to after otka migration
Sponsor 2FA | 1 | NA | Cole K | In Progress
Student Email Verification | 2 | NA | Cole K | In Progress